TIPPECANOE HOUSING SOLUTIONS COALITION

Tippecanoe Housing Solutions Coalition

Decreasing Substandard Housing Task Force

10/9/2

- Discussion Items

  - Reinforce Minimum Habitability Standards

    - Focus on heating, ventilation, plumbing, and pest control.

    - Consider applicability to both rental and owner-occupied housing.

    - Update: Lafayette and West Lafayette staff are drafting a Standard Operating Procedure for emergency responders to report substandard housing internally.

    - Kara and Chad provided a copy of the SOP for review by the group. Feedback was requested. No feedback was provided:

    - Next Steps: Kara and Chad will meet with respective emergency responders to roll out the SOP.

  - Update Local Property Maintenance Ordinances

    - Goal: Align with current health and safety standards across jurisdictions.

    - Update: Lafayette and West Lafayette to schedule a joint city/county meeting on property maintenance code adoption.

      - West Lafayette, Lafayette, Tippecanoe County Health Department, Tippecanoe County Building Commissioner, and Tippecanoe County Zoning Enforcement met on September 29, 2025.

      - West Lafayette and Lafayette use both Unsafe Building Law (UBL) and International Property Maintenance Code (IPMC) to enforce. County Building Commissioner enforces heating, ventilation and plumbing use UBL to enforce.

        - Issue – under UBL can rely on IPMC requirements to enforce houses in disrepair. If only using UBL must be unsafe.

        - Lafayette shared UBL resources with the County.

      - No housing inspection program in County.

        - West Lafayette – proactive rental inspection program.

        - Lafayette – complaint based housing inspection program.

        - County – no housing inspection program

      - Complaint Form

        - West Lafayette – utilize SeeClickFix

        - Lafayette – online and paper form

        - County

          - Zoning – online form

          - Tippecanoe County Health Department – email

          - Building Commissioner – open to exploring online form currently no complaint process

      - Biggest barrier to expanding enforcement -

        - Capacity

        - SB1

    - Next Steps: Prosperity Indiana to:

      - Facilitate listening session to assist with messaging regarding the impact of SB1 on housing habitability.

      - Connect Lafayette and West Lafayette via email introduction to Center for Community Progress regard VAD efforts.

  - Expand and Simplify Public Reporting of Substandard Housing

    - Create more accessible tools for reporting (online, paper forms, flyers).

    - Encourage homeowners to seek assistance when issues arise.

    - Update: Lafayette and West Lafayette will develop a paper flyer for requesting housing inspections.

    - Next Steps: January 1, 2026, City of Lafayette to roll out new website, new online and paper housing inspection form and updated property maintenance codes.

  - Landlord & Property Manager Registry

    - Explore development of a public registry to track recurring or unaddressed deficiencies.

    - Discuss transparency goals, data collection methods, and long-term feasibility.

    - Update: Megan to identify supports needed for Property Partners to align with task force goals and strengthen current efforts.

      - Megan was not in attendance.

    - Next Steps: Follow up with Megan to see how the task force can support Property Partners.

  - Public Awareness & Education

    - Coordinate with the Increasing Housing Stock Task Force on a joint communications campaign.

    - Messaging to address tenants, landlords, property managers, and homeowners.

    - Update: Kara to connect Nathan, Ebony, and Michelle with the Increasing Housing Stock Task Force to begin planning campaign strategy.

      - Increased Housing Task Force working on sub-committee formation. Will follow up with our group once they have an update.

      - United Way to be the coordinate communication plan for the various task force groups.

    - Next Steps: Follow up with United Way and other task force groups to connect communication team volunteers from this task force.

  - Impact of efforts on owner occupied properties.

    - Biggest barrier for owner occupied is funding and education.

      - Education barrier – West Lafayette

      - Funding barrier – Lafayette

    - Home equity loan tailored to medium income households could assist elderly homeowners aging in place.

    - Next Steps:

      - Chad to follow up with West Lafayette Parks and Britton to discuss outreach efforts during elderly programming.

      - Connect with local banks to discuss tailored product for medium income households.

- Next Meetings

  - November - will follow up with an email update regarding progress toward next steps.

  - December meeting is cancelled.

  - Next in person/Teams meeting January 8, 2026.